## Project objectives and results
Strategic objectives
Total Concept method becoming a market driver for large scale energy retrofitting of non-residential buildings in the participating countries and beyond the target countries leading to considerable reduction of energy demand in this building sector.
Considerably reduce the energy demand in the sector of existing non-residential buildings in the participating countries and beyond the target countries.
Resolving the barriers for finding economically profitable solutions for investments for energy performance improvements in the non-residential building sector.
Accelerate the refurbishment of existing non-residential buildings towards Nearly Zero-Energy Buildings in Several European countries.
Increased cooperation between the different stakeholders in the energy performance improvement process, i.e. public and private property owners, property managers, maintenance staff, tenants, architects, consultants, construction companies for gaining the best results in energy savings.
Continuous knowledge transfer and training for the important stakeholders and key actors in the building energy performance improvement process.
Spread the outcomes from the TOTAL CONCEPT project in order to give uptake in large part of European countries.
Total Concept method introduced and adapoted to the national conditions of each participating country and ready to be implemented by the stakeholders and key actors involved in the energy refurbishment process.
Promote the cost-efficient energy retrofitting in existing non-residential buildings based on the Total Concept method so that it will be implemented both in the public and private sector in the participating countries
Develop further the Total Concept method and tools needed for adapting it to national conditions. The Total Concept method will be customised to fit the needs of a participating country in particular
Apply and demonstrate the Total Concept method with pilot projects in participating countries
Develop materials and tools needed for know-how transfer and carrying out trainings and workshops for implementing the Total Concept method in the participating countries on a broader scale
Improve awareness of and know-how about cost-efficient energy retrofitting in existing buildings together with necessary associated education and training. These activities are targeted at local authorities, financing institutions, property owners, developers, architects, consultants and construction companies
Provide general recommendation for the Total Concept method future implementation on an European scale
Detailed information materials, national guidelines and a tool-kit available for the Total Concept method implementation in each participating countries, targeting the different stakeholders and key actors in the participating countries.
(at least 500 downloads of developmed materials)
Pilot studies carried out and cost- efficient action packages based on Total Concept method developed for about 15-18 existing non-residential buildings and a practical implementation is carried out in about 6-8 demonstration buildings. Results show energy reduction of at least 50-70%. (at least 500 downloads of WP3 and WP4 reports)
Practical know-how is transferred to the stakeholders and key actors, new knowledge is made available and replication is stimulated. 2 national training courses are carried out in each participating country and at least 500 stakeholders and key actors will be trained within the project.
High level dissemination activities, including promotion, seminars and Total Concept workshops/meetings for the stakeholders and key actors for implementing the Total Concept in the participating countries.
2 national training courses in each participating country (50-100 participants/course)
1-2 national seminars in each participating country (50-100 participants/seminar)
for local authorities and other stakeholders in the targe group
National help desk service provided to support the replications
10 000 printed leaflets nad 3000 high quality brochures distributed
project website with at least 2000 visitors during the project duration
4 e- newsletters distributed
5-6 Total Concept working meetings for key actors and stakeholders within the project consortium
presentations at national conferences /seminars, articles published in trade journals
At least 10-15 concrete expressions of interest from relevant stakeholders in each participating country to try out and implement the Total Concept method.
Overall recommendations reported for the general European applications of the Total Concept method , common guidelines and tools available to support the Total Concept method implementation on broader scale. (at least 100 downloaded reports and information materials outside the participating countries)
Project objectives
Specific objectives
Main outputs

## Project stakeholders
Target groups and key actors of the project
Real estate companies,
building owners,
companies investing in the energy performance improvements (ESCO)
Results
Project implementation
Primary
Secondary
Consultants and engineers working with energy performance improvements
Representatives from local and national authorities
Trade association of construction clients
Trade association of HVAC engineers
Consultants and engineers working with energy performance improvements in pilot studies
Contractors and technology providors involved in retrofitting of non-residential buildings
Property owners and building maintenance staff involved with pilot studies
Institutes (training and dissemination)
BELOK members
Contractors and technology providors involved in retrofitting of non-residential buildings

## Project time budget
Work packages | Distribution of hours per work package and participant | [8 empty] | Total | Total (%)
| CIT (SE) | SBI/AAU (DK) | Ramboll (DK) | SINTEF (NO) | RKAS (EST) | DACC (DK) | EKVÜ (EST) | SCC (SE) | Bionova (FI)
WP 1 leader | 680 | [8 empty] | 680
WP 1.1-1.4 | 170 | 140 | 110 | 140 | 110 | 120 | 140 | 110 | 140 | 1180
WP 1 total | 850 | 140 | 110 | 140 | 110 | 120 | 140 | 110 | 140 | 1860 | 10.57%
WP 2 leader | [7 empty] | 70 |  | 70
WP 2 | 430 | 150 | 60 | 150 | 60 | 50 | 150 | 60 | 150 | 1260
WP 2 total | 430 | 150 | 60 | 150 | 60 | 50 | 150 | 130 | 150 | 1330 | 7.561%
WP 3 leader |  |  |  | 120 | [5 empty] | 120
WP 3.1 | 50 |  | 50 | 75 | 50 | 25 | 25 | 25 | 50 | 350
WP 3.2 | 50 |  |  | 50 | 25 | 50 | 25 | 50 | 50 | 300
WP 3.3 | 300 | [8 empty] | 300
WP 3.4 | 600 | 200 | 700 | 900 | 250 |  | 600 |  | 700 | 3950
WP 3.5 | 300 | 100 | 200 | 300 | 300 |  | 150 |  | 300 | 1650
WP 3 total | 1300 | 300 | 950 | 1445 | 625 | 75 | 800 | 75 | 1100 | 6670 | 37.92%
Wp 4 Leader | [6 empty] | 100 |  |  | 100
WP 4.1 | 50 | 50 | 20 | 50 | 20 | 20 | 80 | 20 | 50 | 360
WP 4.2 | 170 | 100 | 20 | 100 | 20 | 20 | 120 | 20 | 100 | 670
WP 4.3 | 50 | 50 |  | 50 |  |  | 80 |  | 50 | 280
WP 4 total | 270 | 200 | 40 | 200 | 40 | 40 | 380 | 40 | 200 | 1410 | 8.016%
WP5 leader |  | 100 | [7 empty] | 100
WP 5.1 | 80 | 200 | 20 | 80 | 20 | 50 | 80 | 50 | 80 | 660
WP 5.2 | 70 | 70 | 50 | 70 | 50 | 50 | 70 | 50 | 70 | 550
WP 5.3 | 100 | 100 | 90 | 130 | 80 | 180 | 160 | 50 | 160 | 1050
WP 5.4 | 20 | 20 |  | 20 |  |  | 20 |  | 20 | 100
WP 5 total | 270 | 490 | 160 | 300 | 150 | 280 | 330 | 150 | 330 | 2460 | 13.99%
WP 6 leader | [5 empty] | 100 |  |  |  | 100
WP 6.1 | 20 | 20 |  | 20 |  | 20 | 20 |  | 20 | 120
WP 6.2 |  |  |  | 40 |  | 40 | 40 | 180 | 40 | 340
WP 6.3 | 30 | 30 | 10 | 80 | 10 | 180 | 80 | 120 | 80 | 620
WP 6.4 | 100 | 100 | 30 | 150 | 30 | 70 | 100 | 70 | 150 | 800
WP 6.5 | 100 | 100 | 30 | 100 | 30 | 100 | 100 | 80 | 100 | 740
WP 6.6 | 90 | 90 |  | 90 |  |  | 60 |  | 90 | 420
WP 6.7 | 70 | 70 | 35 | 70 | 35 | 35 | 35 | 30 | 70 | 450
WP 6.8 | 10 | 10 | 10 | 10 | 10 | 30 | 10 | 10 | 10 | 110
WP 6 total | 420 | 420 | 115 | 560 | 115 | 575 | 445 | 490 | 560 | 3700 | 21.03%
WP 7 | 160 | [8 empty] | 160
WP 7 total | 160 | [8 empty] | 160 | 0.9096%
Total | 3700 | 1700 | 1435 | 2795 | 1100 | 1140 | 2245 | 995 | 2480 | 17590
Total (%) | 21.03% | 9.665% | 8.158% | 15.89% | 6.254% | 6.481% | 12.76% | 5.657% | 14.1% | 100%

## Work plan in time scale
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
A 2014 | M 2014 | J 2014 | J 2014 | A 2014 | S 2014 | O 2014 | N 2014 | D 2014 | J 2015 | F 2015 | M 2015 | A 2015 | M 2015 | J 2015 | J 2015 | A 2015 | S 2015 | O 2015 | N 2015 | D 2015 | J 2016 | F 2016 | M 2016 | A 2016 | M 2016 | J 2016 | J 2016 | A 2016 | S 2016 | O 2016 | N 2016 | D 2016 | J 2017 | F 2017 | M 2017
2016
2015
2014
2017
Task 2.1 Development of information materials and carrying out internal training
Task 4.2 Development of national guidelines and improvements in the Total Concept tool-kit
Task 4.1 National evaluations of the pilot studies
Task 3.5 Implementation of Step 2 and Step 3 in pilot study buildings
Task 3.4 Implementation of Step 1 in pilot study buildings
Task 3.3 Carrying out a demonstration project
Task 3.2 Involvement of stakeholders and key actors
Task 3.1 The selection of buildings for pilot studies
Task 2.4 Development of a tool-kit for Total Concept implementation
Task 2.3 Survey of the local conditions and prerequisites for Total Concept implementation
Task 2.2 Breaking the non-technical barriers
Task 4.3 Overall recommendations for Total Concept method implementation on an European scale
Task 5.1 Development of the training materials
Task 5.2 National training courses on the Total Concept method
Task 5.3 Establishing help desk for Total Concept method implementation
Task 5.4 Planning the continuation of the trainings and knowledge transfer
Task 6.5 Total Concept working meetings
Task 6.4 Seminars for the stakeholders in the target groups
Task 6.3 Production of dissemination materials
Task 6.2 Establishing a project website
Task 6.1 Dissemination and communication plan
Task 6.6 Presentations at the international and national conferences, seminars and fairs
Task 6.7 Articles in different journals/magazines in each country
Task 6.8 Preparation of further dissemination
Project start
Project finish
Note on C82: mariliis: Project start date 11 of March 2014
Note on AL82: mariliis: Project end date 10th of March 2017. This means that all the deliverables must be delivered by this date.

## Critical task line
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
A 2014 | M 2014 | J 2014 | J 2014 | A 2014 | S 2014 | O 2014 | N 2014 | D 2014 | J 2015 | F 2015 | M 2015 | A 2015 | M 2015 | J 2015 | J 2015 | A 2015 | S 2015 | O 2015 | N 2015 | D 2015 | J 2016 | F 2016 | M 2016 | A 2016 | M 2016 | J 2016 | J 2016 | A 2016 | S 2016 | O 2016 | N 2016 | D 2016 | J 2017 | F 2017 | M 2017
2017
Task 2.1 Development of information materials and carrying out internal training
Task 4.2 Development of national guidelines and improvements in the Total Concept tool-kit
Task 4.1 National evaluations of the pilot studies
Task 3.5 Implementation of Step 2 and Step 3 in pilot study buildings
Task 3.4 Implementation of Step 1 in pilot study buildings
Task 3.3 Carrying out a demonstration project
Task 3.2 Involvement of stakeholders and key actors
Task 3.1 The selection of buildings for pilot studies
Task 2.4 Development of a tool-kit for Total Concept implementation
Task 2.3 Survey of the local conditions and prerequisites for Total Concept implementation
Task 2.2 Breaking the non-technical barriers
Task 4.3 Overall recommendations for Total Concept method implementation on an European scale
Task 5.1 Development of the training materials
Task 5.2 National training courses on the Total Concept method
Task 5.3 Establishing help desk for Total Concept method implementation
Task 5.4 Planning the continuation of the trainings and knowledge transfer
Task 6.5 Total Concept working meetings
Task 6.4 Seminars for the stakeholders in the target groups
Task 6.3 Production of dissemination materials
Task 6.2 Establishing a project website
Task 6.1 Dissemination and communication plan
Task 6.6 Presentations at the international and national conferences, seminars and fairs
Task 6.7 Articles in different journals/magazines in each country
Task 6.8 Preparation of further dissemination
Note on C90: mariliis: Project start date 11 of March 2014
Note on AL90: mariliis: Project end date 10th of March 2017. This means that all the deliverables must be delivered by this date.

## Schedule Cantt
| duration of the project (in months) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP / Project phase | bar: 1; 36
|  | A 2014 | M 2014 | J 2014 | J 2014 | A 2014 | S 2014 | O 2014 | N 2014 | D 2014 | J 2015 | F 2015 | M 2015 | A 2015 | M 2015 | J 2015 | J 2015 | A 2015 | S 2015 | O 2015 | N 2015 | D 2015 | J 2016 | F 2016 | M 2016 | A 2016 | M 2016 | J 2016 | J 2016 | A 2016 | S 2016 | O 2016 | N 2016 | D 2016 | J 2017 | F 2017 | M 2017
WP 1: | Management (CIT)
Task 1.1 | Management structure of the project and responsibilities | bar: 1
D1.1
Task 1.2 | Communication within the consortium and with external stakeholders
Task 1.3 | Project coordination and administration
|  | D1.3 |  |  | D1.3 |  |  |  |  | D1.3 | [5 empty] | D1.3 | [5 empty] | D1.3 | [5 empty] | D1.3 | [6 empty] | D1.3
Task 1.4 | Organization of meetings and internal project workshops
|  |  | D1.2 |  |  | D1.2 |  |  |  |  | D1.2 | [5 empty] | D1.2 | [5 empty] | D1.2 | [5 empty] | D1.2 | [6 empty] | D1.2
| Total hours | 1: 210; 10: 280; 22: 280; 34: 80
WP 2: | Development of the tool-kit for the Total Concept method application (SCC) | bar: 1 to 7
Task 2.1 | Development of information materials and carrying out an internal workshop on Total Concept method applications | bar: 1 to 4
[5 empty] | D2.1; D2.3 | D2.4
170h
Task 2.2 | Breaking the non technical barriers | bar: 1 to 6
D2.5
40h
Task 2.3 | Survey of the local conditions and prerequisites for adopting the Total Concept method in the participating countries | bar: 1 to 6
D2.6
40h
Task 2.4 | Development of a tool-kit for the Total Concept method implementation | bar: 1 to 7
[7 empty] | D2.7 | D2.8
180h
| Total hours | 1: 430; 10: 0; 22: 0; 34: 0
WP 3: | National pilot projects (SINTEF)
Task 3.1 | The selection of buildings for the pilot studies | bar: 1 to 6
D3.1
50
Task 3.2 | Involvement of the stakeholder and key actors | bar: 1 to 12
50
Task 3.3 | Carrying out a demonstration project | bar: 1 to 12
300
Task 3.4 | Implementation of Step 1 in the Total Concept method in pilot study buildings | bar: 7 to 14
D3.2
600
Task 3.5 | Implementation of Step 2 and 3 in pilot study buildings | bar: 12 to 34
[26 empty] | D3.3 | [8 empty] | D3.4
300
| Total hours | 1: 710; 10: 420; 22: 140; 34: 30
WP 4: | Evaluation and recommendations (EKVÜ) | bar: 13 to 35
Task 4.1 | National evaluations of the pilot studies | bar: 13 to 35
[21 empty] | D4.1 | [14 empty] | D4.2
50
Task 4.2 | Development of national guidelines and improvements in the Total Concept tool-kit | bar: 13 to 35
[24 empty] | D4.3; D4.4 | D4.5 | [10 empty] | D4.3; D4.4; D4.5
170
Task 4.3 | Overall recommendation for the general Total Concept method implementation on an European scale | bar: 25 to 35
D4.6
50
| Total hours | 1: 0; 10: 80; 22: 150; 34: 40
| duration of the project (in months) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
WP / Project phase | bar: 0 1; 40 36
|  | A 2014 | M 2014 | J 2014 | J 2014 | A 2014 | S 2014 | O 2014 | N 2014 | D 2014 | J 2015 | F 2015 | M 2015 | A 2015 | M 2015 | J 2015 | J 2015 | A 2015 | S 2015 | O 2015 | N 2015 | D 2015 | J 2016 | F 2016 | M 2016 | A 2016 | M 2016 | J 2016 | J 2016 | A 2016 | S 2016 | O 2016 | N 2016 | D 2016 | J 2017 | F 2017 | M 2017
WP 5: | Implementation and training on national level (SBI/AAU) | bar: 80 19 to 40 35
Task 5.1 | Development of the training materials for the Total Concept method applications | bar: 80 19 to 150 25
D5.1; D5.2
80
Task 5.2 | National training courses on the Total Concept method | bar: 150 25 to 40 35
D5.3
70
Task 5.3 | Establishing help desks for Total Concept method implementation | bar: 80 19 to 40 35
D5.4
100
Task 5.4 | Planning the continuation of the trainings and knowledge transfer beyond project frames | bar: 150 33 to 40 35
20h
| Total hours | 0 1: 0; 80 10: 50; 150 22: 170; 40 34: 50
WP 6: | Communication and dissemination (DACC)
Task 6.1 | Dissemination and communication planning
|  |  |  | D6.1; D6.2 | [6 empty] | D6.2 | [7 empty] | D6.2 | [8 empty] | D6.2 | [7 empty] | D6.2
20h
Task 6.2 | Establishing a project website | bar: 0 1 to 0 5
D6.3
0
Task 6.3 | Prodution of dissemination materials | bar: 0 5 to 40 35
[10 empty] | D6.4 |  |  |  |  | D6.6 | [6 empty] | D6.5 | D6.6 | [5 empty] | D6.6 | [6 empty] | D6.6
30
Task 6.4 | Seminars for the stake holders in the target group | bar: 80 19 to 40 35
[23 empty] | D6.7 | [12 empty] | D6.8
100h
Task 6.5 | Total Concept working meetings
[6 empty] | D6.9 |  |  |  |  | D6.9 | [5 empty] | D6.9 | [5 empty] | D6.9 | [5 empty] | D6.9 | [6 empty] | D6.10
100h
Task 6.6 | Presentations at international and national conferences, seminars or fairs | bar: 80 19 to 40 35
D6.11
90
Task 6.7 | Articles in different journals/magazines on national and international level | bar: 80 19 to 40 35
D6.12
70
Task 6.8 | Preparation of further dissemination beyond the project frames | bar: 40 34 to 40 35
D6.13
10h
| Total hours | 0 1: 40; 80 10: 90; 150 22: 220; 40 34: 70
WP 7: | IEE Common Dissemination Activities (CIT)
Task 7.1 | Contribution, to the development of information material
Task 7.2 | Participation and/or contribution to information, training and dissemination events
Task 7.3 | Delivery of an update/further input of the action's contribution to the "IEE Common performance indicators"
| Total hours | 0 1: 40; 80 10: 50; 150 22: 50; 40 34: 20
Project meetings | bar: 0 1; 0 4; 0 9; 80 15; 80 21; 150 27; 40 34
Project reports to EACI |  | 80 10: PR; 80 19: IR; 150 28: PR; 40 36: FR
Project Information Sheet & Slides to EACI | bar: 0 2; 80 10; 80 19; 150 30
| Total budget | 0 1: 1430; 80 10: 970; 150 22: 1010; 40 34: 290
|  |  | M | Milestones
|  |  | D | Deliverables
Note on C4: mariliis: Project start date 11 of March 2014
Note on AL4: mariliis: Project end date 10th of March 2017. This means that all the deliverables must be delivered by this date.
Note on C7: Consortium agreement
Note on C11: Risk assessment on the progress of the case studies (step 1, step 2 and step 3)
Note on F11: Risk assessment on the progress of the case studies (step 1, step 2 and step 3)
Note on K11: Risk assessment on the progress of the case studies (step 1, step 2 and step 3)
Note on Q11: Risk assessment on the progress of the case studies (step 1, step 2 and step 3)
Note on W11: Risk assessment on the progress of the case studies (step 1, step 2 and step 3)
Note on AC11: Risk assessment on the progress of the case studies (step 1, step 2 and step 3)
Note on AJ11: Risk assessment on the progress of the case studies (step 1, step 2 and step 3)
Note on D13: Minutes and documents of the coordination meeting 1 ;
Note on G13: Minutes and documents of the coordination meeting 2
Note on L13: Minutes and documents of the coordination meeting 3
Note on R13: Minutes and documents of the coordination meeting 4
Note on X13: Minutes and documents of the coordination meeting 5
Note on AD13: Minutes and documents of the coordination meeting 6
Note on AK13: Minutes and documents of the coordination meeting 7
Note on F17: Information materials on the Total Concept method and its application; Materials needed for carrying out an internal workshop within project consortium
Note on G17: Minutes and documents of the internal workshop
Note on H20: A publishable report describing existing non technical barriers and suggestions for overcoming them
Note on H23: A publishable report on the local conditions and prerequisites for adopting Total Concept method in the participating countries
Note on H26: One common tool-kit for Total Concept method applications in English
Note on I26: A Tool-kit for the Total Concept method applications on a national level in each participating country
Note on H31: Internal report on the selected buildings for the pilot studies and identified stakeholders and key actors for the Total Concept pilot implementation
Note on Q38: Reports on the results of implementation of Step 1 in the Total Concept working method in the pilot buildings.
Note on AA41: Internal report on the results of implementation of Step 2 in the Total Concept working method in the pilot buildings
Note on AJ41: Reports on the results of the implementation of the Total Concept working method in the pilot study buildings.
Note on V46: An internal report on the preliminary results of the implementation of the Total Concept in the different participating countries.
Note on AK46: A publishable report on the evaluation of the results of the national pilot projects in the different participating countries.
Note on O47: mariliis: together with coordination
Note on Y49: Updated information materials on the Total Concept method and its application; Updated common tool-kit for the Total Concept method implementation.
Note on Z49: Updated tool-kit for the Total Concept method implementation on a national level in each participating country.
Note on AK49: D4.3.Reports on the results of implementation of Step 1 in the Total Concept working method in the pilot buildings. D4.4 Updated commong tool-kit for the Total Concept method implementation. D4.5. Updated tool-kit for the Total Concept method implementation on a national level in each participating country.
Note on O50: mariliis: together with coordination
Note on AK52: Report on the Total Concept working method applications on an European scale.
Note on C57: mariliis: Project start date 11 of March 2014
Note on AL57: mariliis: Project end date 10th of March 2017. This means that all the deliverables must be delivered by this date.
Note on AA60: Training materials for training the stakeholders in the target groups of the Total Concept method. // Collection of course materials given in the trainings to the specific target groups in the Total Concept method applications.
Note on AK63: Evaluation reports of the training courses held in each participating country, including a list of participants, minutes of the training sessions and summary of the feedback.
Note on AK66: Evaluation reports on the Total Concept method help desk activities.
Note on E73: Dissemination plan // Reports for dissemination planning, reporting, evaluation, documentation in each participating country.
Note on L73: Reports for dissemination planning, reporting, evaluation, documentation in each participating country.
Note on T73: Reports for dissemination planning, reporting, evaluation, documentation in each participating country.
Note on AC73: Reports for dissemination planning, reporting, evaluation, documentation in each participating country.
Note on AK73: Reports for dissemination planning, reporting, evaluation, documentation in each participating country.
Note on G76: Project website with online workspace
Note on K79: A leaflet promoting the Total Concept method and targeted to the main stakeholders in each participating country.
Note on P79: E-newsletters in four editions in English and national languages
Note on W79: An information brochures promoting the Total Concept method and project outcomes.
Note on X79: E-newsletters in four editions in English and national languages
Note on AD79: E-newsletters in four editions in English and national languages
Note on AK79: E-newsletters in four editions in English and national languages
Note on X82: Presentation materials at seminars targeting local authorities and other important stakeholders in each participating country.
Note on AK82: Evaluation reports of national seminars held in each participating country, including a list of participants, minutes of the seminars and summary of the feedback. One report per country and in English.
Note on G85: Presentation materials at Total Concept working meetings
Note on L85: Presentation materials at Total Concept working meetings
Note on R85: Presentation materials at Total Concept working meetings
Note on X85: Presentation materials at Total Concept working meetings
Note on AD85: Presentation materials at Total Concept working meetings
Note on AK85: Evaluation reports of Total Concept working meetings, including a list of participants, minutes of the training sessions and summary of the feedback.
Note on AA88: Presentation materials at national and international conferences, seminars or fairs. In native languages and in English
Note on AK91: Articles in journals and magazines in each country and in international magazines/conference proceedings
Note on AK94: Report about the dissemination plan and the continuation of the trainings beyond the project lifetime.
Note on AL105: Final publishable report

## Milestones and deliverables
Milestones and deliverables
Nr | Description | Type and format | Responsible | Dissem. level | Deadline
D1.1 | Consortium agreement | Printed contract in EN | CIT | Internal | 2014-04-01
D1.4 | Risk assessment on pilot projects | Report, electronic, EN | CIT | Internal | 2014-04-01
D1.2 | Minutes and documents of the coordination meetings | Paper, electronic, EN | CIT | Internal | 2014-05-01
D6.1 | Dissemination plan | Paper, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | Internal | 2014-06-01
D6.2 | Reports for dissemination planning, reporting, evaluation, documentation (covering tasks 6.3- 6.7) in each participating country. | Paper, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | Internal | 2014-06-01
D7.1 | Set of updated IEE Common Performance indicators including their baseline and assumptions for extrapolation | paper, electronic, EN | CIT | Internal | 2014-06-01
M1 | Information materials on the Total Concept method and its application ready |  | CIT |  | 2014-07-14
D2.1 | Information materials on the Total Concept method and its application. | Paper, electronic, EN | CIT | public | 2014-07-01
D2.3 | Materials needed for carrying out an internal workshop within the project consortium. | Slides, electronic, EN | CIT | Internal | 2014-07-01
M2 | Outcomes from the national evaluations of non-technical barriers and local conditions for Total Concept implementations recieved. |  | SBI/AAU, SINTEF, SCC, EKVÛ, Bionova |  | 2014-08-14
M3 | Internal workshop carried out |  | CIT |  | 2014-08-14
D1.2 | Minutes and documents of the coordination meetings | Paper, electronic, EN | CIT | Internal | 2014-08-01
D1.4 | Risk assessment on pilot projects | Report, electronic, EN | CIT | Internal | 2014-08-01
D2.4 | Minutes and documents of the internal workshop | Paper, electronic, EN | SCC | Internal | 2014-08-01
D6.3 | Project website | website/webtool, EN | SCC | public | 2014-08-01
D6.9 | Presentation materials at Total Concept working meetings | Slides, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | public | 2014-08-01
D2.2 | Digital help tools needed for supporting the Total Concept method applications. | Software, electronic, EN | CIT | public | 2014-09-01
D2.5 | A publishable report describing existing non technical barriers and suggestions for overcoming them | Paper, electronic, EN | SCC | public | 2014-09-01
D2.6 | A publishable report on the local conditions and prerequisites for adopting Total Concept method in the participating countries | Paper, electronic, EN | SCC | public | 2014-09-01
M4 | Common tool-kit for the Total Concept method application |  | CIT |  | 2014-09-01
D2.7 | One common Tool-kit ready for the Total Concept method applications | paper, software, EN | CIT | public | 2014-09-01
M5 | Pilot buildings selected and key actors and stakeholders involved |  | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova |  | 2014-09-01
D3.1 | Internal report on the selected buildings for the pilot studies and identified stakeholders and key actors for the Total Concept pilot implementation | Paper, electronic, EN | SINTEF | Internal | 2014-09-01
M6 | National tool-kits ready for the Total Concept method application and national pilot studies started |  | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova |  | 2014-10-01
D2.8 | A Tool-kit for the Total Concept method application on a national level in each participating country | paper, Software, local language | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova | public | 2014-10-01
D1.4 | Risk assessment on pilot projects | Report, electronic, EN | CIT | Internal | 2014-12-01
D6.2 | Reports for dissemination planning, reporting, evaluation, documentation (covering tasks 6.3- 6.7) in each participating country. | Paper, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | Internal | 2014-12-01
D6.4 | A leaflet promoting the Total Concept method and targeted to the main stakeholders in each participating country | printed folder EN + local languages | DACC, SCC, SINTEF, EKVÛ, Bionova | public | 2014-12-01
M7 | Step 1 in Total Method in first pilot study buildings finished and Step 2 ready to be excecuted in each participating country |  | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova |  | 2015-01-15
D1.2 | Minutes and documents of the coordination meetings | Paper, electronic, EN | CIT | Internal | 2015-01-01
D6.9 | Presentation materials at Total Concept working meetings | Slides, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | public | 2015-01-01
D6.6 | E-newsletters in four editions | digital newaletter EN + local languages | DACC, SCC, SINTEF, EKVÛ, Bionova | public | 2015-03-01
D1.4 | Risk assessment on pilot projects | Report, electronic, EN | CIT | Internal | 2015-06-01
M8 | Step 1 in Total Method concept finished and reported in all pilot buildings in each participating country |  | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova |  | 2015-06-01
D3.2 | Reports on the results of implementation of Step 1 in the Total Concept working method in the pilot buildings. 1 publishable fact sheet for each pilot study building in English and native language and 1 detailed report in native languages of each participating country. | Paper, electronic, EN+ local language | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova, Ramböll, RKAS | public | 2015-06-01
D1.2 | Minutes and documents of the coordination meetings | Paper, electronic, EN | CIT | Internal | 2015-07-01
D6.9 | Presentation materials at Total Concept working meetings | Slides, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | public | 2015-07-01
D6.2 | Reports for dissemination planning, reporting, evaluation, documentation (covering tasks 6.3- 6.7) in each participating country. | Paper, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | Internal | 2015-09-01
M9 | Step 2 in Total Method in first pilot study buildings finished and Step 3 ready to be excecuted in each participating country |  | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova |  | 2015-10-01
M10 | First evaluations of the outcomes from Step1 and Step 2 ready in ech participating country |  | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova |  | 2015-11-01
D4.1 | An internal report on the implementation of the Total Concept in the different participating countries. | Paper, electronic, EN | EKVÛ | Internal | 2015-11-01
D1.4 | Risk assessment on pilot projects | Report, electronic, EN | CIT | Internal | 2015-12-01
D6.5 | An information brochures promoting the Total Concept method and project outcomes. | printed brochure EN + local languages | DACC, SCC, SINTEF, EKVÛ, Bionova | public | 2015-12-01
D1.2 | Minutes and documents of the coordination meetings | Paper, electronic, EN | CIT | Internal | 2016-01-01
D6.6 | E-newsletters in four editions | digital newaletter EN + local languages | DACC, SCC, SINTEF, EKVÛ, Bionova | public | 2016-01-01
M11 | Presentation materials ready for seminars targeting local authorities and stakeholders in each country |  | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova |  | 2016-01-01
D6.7 | Presentation materials at seminars targeting local authorities and other important stakeholders in each participating country. | Slides, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | public | 2016-01-01
D6.9 | Presentation materials at Total Concept working meetings | Slides, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | public | 2016-01-01
D4.3 | Updated information materials on the Total Concept method and its application. | Paper, electronic, EN | CIT | public | 2016-02-01
D4.4 | Updated common tool-kit for the Total Concept method implementation. | paper, Software, EN | CIT | public | 2016-02-01
D4.5 | Updated tool-kit for the Total Concept method implementation on a national level in each participating country. | paper, Software, local language | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova | public | 2016-03-01
M12 | Mid evaluation of outcomes from Step 2 ready in each participating country |  | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova |  | 2015-11-01
D3.3 | Internal report on the results of the implementation of the Step 2 of the Total Concept working method in the pilot study buildings. | Paper, electronic, EN | SINTEF | Internal | 2016-04-01
M13 | Training and course materials ready for training stakeholders in each participating country |  | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova |  | 2016-04-01
D5.1 | Training materials for training the stakeholders in the target groups of the Total Concept method. | Slides, working paper, EN+national languages | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | Internal | 2016-04-01
D5.2 | Collection of course materials given in the training to the specific target groups in the Total Concept method applications. | Slides, paper, EN+national languages | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | public | 2016-04-01
D6.11 | Presentation materials at national and international conferences, seminars or fairs. | Slides, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | public | 2016-04-01
D1.4 | Risk assessment on pilot projects | Report, electronic, EN | CIT | Internal | 2016-06-01
D6.2 | Reports for dissemination planning, reporting, evaluation, documentation (covering tasks 6.3- 6.7) in each participating country. | Paper, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | Internal | 2016-06-01
D1.2 | Minutes and documents of the coordination meetings | Paper, electronic, EN | CIT | Internal | 2016-07-01
D6.6 | E-newsletters in four editions | digital newaletter EN + local languages | DACC, SCC, SINTEF, EKVÛ, Bionova | public | 2016-07-01
D6.9 | Presentation materials at Total Concept working meetings | Slides, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | public | 2016-07-01
M14 | National seminars for local authorities and stakeholders carried out |  | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova |  | 2016-10-01
M15 | National trainings of stakeholders carried out |  | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova |  | 2016-11-01
D1.4 | Risk assessment on pilot projects | Report, electronic, EN | CIT | Internal | 2017-01-01
M16 | Results of pilot studies finalized |  | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova, Ramböll, RKAS |  | 2016-12-01
D3.4 | Reports on the results of the implementation of the Total Concept working method in the pilot study buildings. 1 publishable fact sheet for each pilot study building in English and native language and 1 detailed report in native languages of each participating country | Paper, electronic, EN+ local language | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova, Ramböll, RKAS | public | 2017-01-01
D1.2 | Minutes and documents of the coordination meetings | Paper, electronic, EN | CIT | Internal | 2017-02-01
D4.2 | A publishable report on the evaluation of the results of the national pilot projects in the different participating countries. | Paper, electronic, EN | EKVÛ | public | 2017-02-01
M17 | Information materials and tool-kit are updated based on the outcomes from the pilot studies |  | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova |  | 2017-01-01
D4.3 | Updated information materials on the Total Concept method and its application. | Paper, electronic, EN | CIT | public | 2017-02-01
D4.4 | Updated common tool-kit for the Total Concept method implementation. | paper, Software, EN | CIT | public | 2017-02-01
D4.5 | Updated tool-kit for the Total Concept method implementation on a national level in each participating country. | paper, Software, local language | CIT, SBI/AAU, SINTEF, EKVÛ, Bionova | public | 2017-02-01
D4.6 | Report on the Total Concept working method applications on an European scale. | Paper, electronic, EN | EKVÜ | public | 2017-02-01
D5.3 | Evaluation reports of the training courses held in each participating country, including a list of participants, minutes of the training sessions and summary of the feedback. | Paper, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | Internal | 2017-02-01
D6.6 | E-newsletters in four editions | digital newaletter EN + local languages | DACC, SCC, SINTEF, EKVÛ, Bionova | public | 2017-02-01
D6.8 | Evaluation reports of national seminars held in each participating country, including a list of participants, minutes of the seminars and summary of the feedback | paper, electronic, EN | DACC, SCC, SINTEF, EKVÛ, Bionova | Internal | 2017-02-01
D6.10 | Evaluation reports of Total Concept working meetings, including a list of participants, minutes of the training sessions and summary of the feedback. | paper, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova, DACC, SCC | Internal | 2017-02-01
D6.12 | Articles in journals and magazines in each country and in international magazines/conference proceedings | paper, printed, EN+ local languages | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova, DACC, SCC, RKAS, Ramböll | public | 2017-02-01
D5.4 | Evaluation reports on the Total Concept method help desk activities | Paper, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | Internal | 2017-03-01
D6.2 | Reports for dissemination planning, reporting, evaluation, documentation (covering tasks 6.3- 6.7) in each participating country. | Paper, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova | Internal | 2017-03-01
M18 | Results of the TOTAL CONCEPT project reported |  | CIT |  | 2017-03-01
D1.3 | Final publishable report | Paper, electronic, EN | CIT | public | 2017-03-01
M19 | Plans for dissemination beyond the project frames are finalized |  | CIT |  | 2017-03-01
D6.13 | A report about the dissemination plan beyond the project continuation | paper, electronic, EN | SBI/AAU, SINTEF, CIT, EKVÛ, Bionova, DACC, SCC | Internal | 2017-03-01

## Risk assessment
No | Possible risks | Probability to occur (scale 1-5, 1=low, 5=high) | Impact on results (scale 1-5, 1=low, 5=high) | Score | Ranking | Possible measures to eliminate the risk | Time to deliver | Reposnsible partner(s)
1 | Internal workshop takes place to late (WP2) (difficulty to set the suitable date and involve subcontractors) | 2 | 4 | 8 | 7 | Plan the workshop in time, involve key actors in time | april-may 2014 | All partners
2 | Tool-kit not ready in time for pilot studies (preparation of guidelines and tools delayed as well as results from task 2.3) | 3 | 3 | 9 | 6 | Plan the work in time, set clear objectives and follow up the work continuously | april-august 2014 | CIT
3 | Operating the Totaltool is difficult for the project partners | 3 | 3 | 9 | 6 | Get feedback from partners during the development | april-august 2014 | CIT
4 | Property owners of pilot study building cancel their participation in the project (requires evaluation per country) (WP3) | EST 2; SE 2; FI 3, NO 1; DK 2 | 5 | EST 10; SE 10; FI 15, NO 5; DK 10 | 4 | Select possible other buildings for plan B. Change buildings between countries | april-june 2014 | Ramböll, SINTEF, CIT, RKAS, Bionova
5 | Difficulty to involve the key actors and stakeholders for pilot studies, pilot studies can not be started in time (requires evaluation per country) (WP3) | 2 | 5 | 10 | 5 | Plan the pilot studies time, contact key actors in time | april-june 2014 | All partners
6 | No suitable pilot study buildings (difficulty to find buildings that fulfil the preset criteria) (requires evaluation per country) (WP3) | EST 2; SE 2; FI 3, NO 1; DK 2 | 5 | EST 10; SE 10; FI 15, NO 5; DK 10 | 4 | Make a plan B and include for example a residential building | april-june 2014 | Ramböll, SINTEF, CIT, RKAS, Bionova
7 | Demonstration building (TASK3.3) delayed or not done | 3 | 3 | 9 | 6 | Plan the work in time, set clear objectives and follow up the work continuously | april-sept 2014 | CIT
8 | Practical implementation of Total Concept method (Step 2) is delayed (requires evaluation per country) (WP3) | 5 | 5 | 25 | 1 | Try to avoid full scale renovations | april-sept 2014 | Ramböll, SINTEF, CIT, RKAS, Bionova
9 | Practical implementation of Total Concept method (Step 2) can not be carried out, property owners change their mind (requires evaluation per country) (WP3) | 3 | 5 | 15 | 4 | Plan to have maximum buildings for Step 1 so that the probability for getting practical implementation would be higher | april-sept 2014 | Ramböll, SINTEF, CIT, RKAS, Bionova
10 | Step 2 in Total Concept method takes too long time and Step 3 can not be excecuted for the full length (12 months) (WP3) | 4 | 5 | 20 | 2 | Have a plan B and in the worst case try to extrapolate the data | april 2014-sept 2015 | Ramböll, SINTEF, CIT, RKAS, Bionova
11 | Pilot studies do not give the expected results (comes from Step 3 are not according to the expected results as planned in Step 1 - planned savings and profitability not recieved)(WP3) | 3 | 3 | 9 | 6 | Make sure that the key actors and stakeholders get the relevant knowledge transfer, carry out continuous follow up | april 2014-sept 2015 | All partners
12 | We do not manage to have in total 15-18 existing non-residential buildings where Step 1 in the Total Concept method is carried out | 2 | 4 | 8 | 7 | Plan to have maximum buildings for Step 1 | april-june 2014 | Ramböll, SINTEF, CIT, RKAS, Bionova
13 | We do not manage to have in total 6-8 demonstration buildings where practical implementation (Step 2 and 3) is carried out | 4 | 4 | 16 | 3 | Plan to have maximum buildings for Step 1 so that the probability for getting practical implementation would be higher | april-sept 2014 | Ramböll, SINTEF, CIT, RKAS, Bionova
14 | Low participation of the key actors and stakeholders in the national trainings (WP5)
15 | The training materials and training sessions do not give the expected results (t.ex. too difficult to understand the content, low feedback grades given by the participants)
16 | The established help desk gets no interest from the stakeholders and key actors (WP5)
17 | Low participation of the key actors and stakeholders in the national seminars (WP6)
18 | Low number of downloads of reports and deliverables from the project website
19 | Low number of visits at the project website
19 | Possible risks | Probability to occur (scale 1-5, 1=low, 5=high) | Impact on results (scale 1-5, 1=low, 5=high) | Score/ Ranking |  | Possible measures to eliminate the risk | Time to deliver | Reposnsible partner(s)
20 | resistance from the target groups (e.g. when the tools are developed outside their country/company they may not be interested. They already have number of tools to use)
21 | reorganisations inside the project
22 | deliverables delayed
Note on H1: mariliis: timeframe when the possible measures should be carried out